## Game play description
Game part | Description
General | The game is a mix of Nuclear Throne with Hotline Miami, both of these are topdown fastpaced shooter games.
Player | The player backstory is still no decided.
Level | In the game, for each level you spawn in an initial room with basic weaponry. He collects new weapons from the level as he progressed.
Lives | The exact ammount of health is not yet decided but it will be low, this so to provide a sense of challenge.
Boss enemy | At the end of each level there are stronger versions of the enemies, these are bosses.
Power-ups | When it comes to power ups, it will mostly be health(med kits). Not decided yet.
Enemies | There will be multiple different sorts of enemies, Melee, With simple weaponry, with more complex weaponry, and finally the boss with a rare weapon that you can take to the next level
…

## Planning
Topic | Priority | Status | Time spent
Avatar
Find spritesheet | High | Finished | 1h
spitesheet ready to use | High | WIP | 3h
Avatar class
function Die | High | Not started
function IsHit | High | Not started
Rock
Prop class | High | WIP | 1h
Find Spritesheet | High | Finished
spitesheet ready to use | High | WIP | 3h
Others
Intro animation | Low | Not started

## Working parts
Functionality | Works since
Level is drawn | 2019-03-04
Avatar can walk through the level | 2019-03-07
Camera follows the avatar | 2019-03-07
Avatar performs all animations correctly | 2019-03-14
Enemies are drawn at the right position in the level | 2019-03-14
…

## Milestone
Working functionality at milestone
Level is drawn
Avatar can walk through the level
Camera follows the avatar
Avatar performs all animations correctly
Enemies are drawn at the right position in the level
Enemies perform their animations and move correctly
Power-ups are drawn at the right position in the level
Power-ups perform their animations and move correctly
Interaction player enemies
…

## Deadline
Working functionality at deadline
Level is drawn
Avatar can walk through the level
Camera follows the avatar
Avatar performs all animations correctly
Enemies are drawn at the right position in the level
Enemies perform their animations and move correctly
Power-ups are drawn at the right position in the level
Power-ups perform their animations and move correctly
Interaction player enemies
…