## Game play description
Game part | Description
General | The game is a mix of Nuclear Throne with Hotline Miami, both of these are topdown fastpaced shooter games.
Player | The player backstory is still not decided.
Level | In the game, for each level you spawn in an initial room with basic weaponry. He collects new weapons from the level as he progressed.
Lives | The exact ammount of health is not yet decided but it will be low, this so to provide a sense of challenge.
Boss enemy | At the end of each level there are stronger versions of the enemies, these are bosses.
Power-ups | When it comes to power ups, it will mostly be health(med kits). Not decided yet.
Enemies | There will be multiple different sorts of enemies, Melee, With simple weaponry, with more complex weaponry, and finally the boss with a rare weapon that you can take to the next level

## Planning
Topic | Priority | Status | Time spent
Player
Finish making sprites | Medium | WIP
Animation for arms | Medium | Not started
Gameobject
Basic behaviour | High | Finished | 4h
Ai
Path finding | High | Finished | 4h
Pickups
Basic behaviour | High | Finished | 1h
Basic Weapon pickups | High | Finished | 2h
Level
Populating the level with static items | High | WIP
Implementing doors | Medium | Not started
Level collisions | High | Finished | 10h
UI and TankScript
Plan the scripting language | High | Finished | 4h
Basic functionality for loading and displaying UI | High | Finished | 10h
Callback system | High | Finished | 4h
Asset preloader for textures and audio | High | Finished | 2h
Scene loader | High | WIP
Others
Menu background | Low | Not started

## Working parts
Functionality | Works since

## Milestone
Working functionality at milestone
Level collisions
Ai can walk through the level with custom pathfinding
Objects can collide with each other
Scripting language used for Ui
Scripting language used for Texture preloading
Scripting language used for Audio preloading
Scripting language used for Scene loading
Complex ui system which allows for fast iteration and ease of functionality through an id and callback system
Pickups that both the player and the ai can pickup
Different weapons that can be picked up and shot by both ai and player, these weapons are pickups
Flexible projectile mechanics
Blood particle system
Player can also drop items
Player controls
Projectiles can do dammage and apply kickback to the object they hit
Game reset
Death screen
Win Screen
Info ui

## Deadline
Working functionality at deadline